Project Plan

Group 6 — Computational Biology Final Project

# Research Question

Can B-factors identify flexible binding-site residues that reduce rigid docking accuracy? We also test whether B-factors can guide ensemble docking selection via the B-factor Index for the binding site (BFIbs).

# Pipeline

Five steps, driven by experiment/main.py

- PDB Survey & B-factor Extraction — Download holo structures of a target (e.g., CDK2); extract per-residue B-factors within 5Å of ligand; compute BFIbs.

- Cross-Docking with Vina — For every receptor A + ligand B (A≠B), run rigid docking; measure RMSD vs crystal pose; classify success (RMSD<2Å) or failure.

- Correlation Analysis — Spearman ρ between receptor B-factors and docking RMSD; t-test comparing B-factors of successful vs failed pairs.

- B-factor–Guided Ensemble Docking — Select ensembles by BFIbs (closest to 1), random (baseline), and lowest BFIbs (most rigid). Compare success rates.

- Ensemble Optimizer Benchmark — Implement literature optimizer (De Paris 2018; Bolstad 2009) as an upper bound for comparison.

# Deliverables

- Paper (6 sections: Intro, Background, Evidence, Experiment, Discussion, Conclusion)

- Presentation slides

- Experiment code + results (CSV in output/, figures in figures/)

# Timeline (14 Days)

- Day 1–2: Install Vina/obabel; survey PDB; select target; download structures

- Day 3–4: Extract B-factors; compute BFIbs; prepare PDBQT files

- Day 5–7: Run cross-docking + ensemble docking; statistical analysis; generate figures

- Day 8–10: Write paper (Intro through Conclusion)

- Day 11–12: Create presentation slides

- Day 13–14: Revise paper; rehearse presentation

# Key References

- Amaro et al. (2018) — Ensemble docking in drug discovery. Biophys. J.

- Halip et al. (2021) — BFIbs to prioritize structures for docking. Struct. Chem.

- Korb et al. (2012) — Potential and limitations of ensemble docking. JCIM.

- Palacio-Rodríguez et al. (2019) — ECR improves ensemble docking. Sci. Rep.

- Bottegoni et al. (2009) — 4D docking. J. Med. Chem.

- Rao et al. (2008) — Improving enrichment through ensemble docking. JCAMD.

- Najmanovich et al. (2000) — Side-chain flexibility. Proteins.

- De Paris et al. (2018) — Selective ensemble optimization. BMC Bioinf.

- Bolstad & Anderson (2009) — Pruning ensembles. JCAMD.

# Key Risks

- Backbone–sidechain decoupling: B-factors measure backbone motion, not side-chain rotations (Najmanovich 2000).

- Target selection: Need structural diversity—too little gives ceiling effects, too much gives floor effects.

- Statistical power: Limited distinct conformations may reduce power. Report effect sizes + CIs.

- Vina limitations: Less accurate than Glide/GOLD/ICM. Cross-validate if time permits.

- Correlation ≠ causation: Confounds: resolution bias, crystal packing, ligand-induced B-factor changes.